## Sheet1
Task | Start Date | End Date | Duration
Background research and investigation | 2023-10-17 | 2023-10-31 | 14
Researching the NextItNet model | 2023-10-24 | 2023-10-31 | 7 | 45418
Prepare Project Proposal | 2023-10-25 | 2023-11-03 | 9
Prepare the installation of the Rebole tool and environment | 2023-10-30 | 2023-11-14 | 15 | 45420
Preparing and Preprocessing Datasets | 2023-10-31 | 2023-11-07 | 7 | 45350
Test models and datasets | 2023-11-14 | 2023-12-04 | 20 |  | 45216 |  | 45284
Prepare Progress Report | 2023-12-04 | 2023-12-24 | 20
Implementation of the model on the first two datasets | 2024-02-28 | 2024-03-10 | 11
Model and parameter adjustment | 2024-03-10 | 2024-03-13 | 3
Implementation of the model on the last three datasets | 2024-03-15 | 2024-03-25 | 10
Model and parameter adjustment | 2024-03-25 | 2024-03-28 | 3
Train the model using 5 different evaluation metrics | 2024-03-28 | 2024-04-10 | 13
Analyze and evaluate results | 2024-04-10 | 2024-04-20 | 10
Feedback and report writing | 2024-04-15 | 2024-05-06 | 21
45418